SCT Banner YES Implementation Team

Meeting Notes

# MEETING LOGISTICS

| Item | Description |
| --- | --- |
| Date | February 18, 2009 |
| Time | 8:30 a.m. |
| Location | MESHEL HALL – Computer Center Conference Room |

ATTENDEES

| Facilitator(s) | Eileen Greaf and Rick Marsico |
| --- | --- |
| Note Taker | Cheryl Beil |
| Participants | Catherine Cala, Mary Lou Castner, Troy Cross, Sue Davis, Becky Geltz, Brian Godson, Tim Kovaleski, Dona Madacsi, Liz Nelson, James Stanger, Steve Taraszewski, Jason Thomas, Bob Tupaj, and Beth Yeatts. |
| Not Present | Jeanne Herman, Betty Jo Licata, Cindy Miller, and Donna Wainio. |

AGENDA  ITEMS

| CORRECTIONS | Notes |
| --- | --- |
| Impl Mtg –12/8/08 | Email any corrections to Cheryl Beil. |
| REVIEW PRIOR ACTION ITEMS |  |
|  | See updates on items #1, 3, 4, 9a and 12. |
| TEAM UPDATES |  |
| Student |  |
| a. Regis/Records | Tim K. reported that PROD will be shut down 3/7 to load ~50,000 student records; will then work on ~29,000 archived student records. Cleanup of records is needed to prepare for Banner 8 implementation. |
| b. Admissions | Sue D. reported that Cameron has basically completed the EMAS bridge; will do one more fix and then will be able to eliminate the M-204 download. |
| c. Student Accts | Beth Y. reported that SAUR staff continues to work on collections in stages, including electronic submission to the Attorney General and the credit bureau, as well as the write-off report; testing should be finished today. Mailed 1098-T forms to students, but must still send the electronic file to IRS; continue to work with the consultant for full implementation. Reworked billing to move completely towards eBilling due to increased cost of postage. Will mail paper bills to students for first billing of each term; thereafter will send paper bills only for outstanding balances or collections. Working on Profile screens to assist with questions. Revised Promise to Pay and are revising the process for cancelled checks. Began meeting weekly with General Acctg to address reconciling Stafford loans and replacement checks. Will meet with consultant this week. |
| Financial Aid | James S. reported that the 2009-10 academic year went live with some extra processing; tracking letters were sent out – currently working on the budgeting and awarding stage. Should be able to create awards by the end of Feb. Will request Computer Center to print 5,000 SAT letters for mailing. Held a conference call with Great Lakes re: a new hold and release process for loans; will not send loans for YSU unless a student file is set up to release loan funds based on actual enrollment and validation. Also participated in a teleconference with Kent State re: GoLive for the year and how each university is handling each of the processes. Liz is updating all of our Ohio scripts since the State phased out one grant program. Chancellor Fingerhut sent a memo to colleges re: possible changes to grant programs for the current year due to a budget shortfall. |
| General Person | Rick M. reported that Bob Forchione will be the new team lead of the General Person Team. Bob will schedule a meeting for the team to identify all open issues. Liz is working on residency code changes involving 8 counties in Pennsylvania to reflect the Board-approved reduction in fees for the Fall 2009 out-of-state registration surcharge. Encountered some problems with permanent addresses being deactivated or listing 2 permanent addresses. Code 4 used to be for International but will now be used for the 8 PA counties. Beth Y. reported that GP addresses are causing significant problems for processing. Several staff are authorized to enter data and modify status. Issue will be compounded with self-service for students. Liz reported on a similar issue with phone numbers. Dona M. will have Bob F. review the matter in depth. |
| HR/Payroll | No report given. |
| MyYSU | Bob T. reported that a small work team was organized to plan for Luminis 4; will address Gmail, Zimbra, portal email, LDI and targeted announcements. There is a possibility of adding more departments after resolving the mass email issue. Currently planning a new design for the portal. Need to draft a Guest Accounts policy. Plan to also review current use of Channels. |
| Finance | Mary Lou reported that 1099’s were run and mailed the end of January. Currently testing the Banner upgrades from 7.2 to 7.3 and 7.4. Distributed test plans to various areas. Focus is on testing feeds into Finance for university receivables, student refunds, mailroom, procurement card and bookstore; goal is to complete testing by tomorrow. |
| Advancement | Catherine C. reported that staff is working with Computer Center on 2 major data needs: 1) data for Phone-a-Thon next week, that triggered completion of download of data from Harris Directory which provided ~15,000 new employer records to update Alumni records; and 2) data for Kresge Challenge mailing that is sent to everyone in data base. The new approach is to mail a postcard with our web address for the online giving site to Graduates between 2004-2008 instead of the traditional letter and pledge card. Recently ran a report of email addresses in system totaling ~46,000 but ~30,000 were campus emails (either employees or students). Catherine wondered whether campus @student.ysu.edu addresses for Alumni were being de-activated after the 1-year free membership period; IT will check further. Currently testing for Banner upgrade; will submit reports. Catherine expressed appreciation for the quality of IBI WebFocus training. |
| Communication (Rick Marsico for BJ Licata) | Rick M. indicated that Ron Cole plans to address the Impl Team at the March meeting to discuss a communication vehicle for technology, in an effort to reduce usage of the portal usage for mass communication. |
| Reporting | Becky G. reported that they are behind on reporting; still fixing data for Summer 2008 before reporting can be done. It was noted that file specifications will change for at least one student file for Summer 2009 regarding student ethnicity. Another issue involves capturing the original county of residency at the time a student enrolls; this data was available in M-204 but not in Banner as a result of how we handled migration of addresses. Becky will contact OBOR to discuss the impact if we are not able to accurately report this data. She reported that the recent audit determined an accuracy rate of 98.5% for reporting out of M-204. |
| Training | No report given. |
| Technical | Troy reported that there will be a MyYSU outage on Sunday 2/22 from 4-8:00 AM for routine maintenance; campus was notified through a portal announcement. Another outage is planned on 2/28 from 8AM-8PM to upgrade all Banner 7 releases in INB and SSB. The student load is planned for 3/7 which will involve another outage. After Banner 7 upgrades are completed, Oracle CPU patches will be done. The plan is to start the ODS 8.1 upgrade in March to bring the system current (this does not require installation of Banner 8). Notice was sent to Team Leaders that Banner 7 will no longer be supported as of 9/1/2010. Planning is underway to upgrade to Luminis 4; the goal is to install prior to Banner 8. Staff is working to have Banner 8 loaded in area test instances by this Summer. Troy inquired whether the existing test instances still require cloning of PROD. Backup is also being done for these 12 instances; areas should notify Troy of any continuing need for cloning or backup of specific test instances. PPRD will be cloned on 2/22 to begin conversion to Banner 7 upgrades on 2/23. Will email team when it is available on 2/25. |
| SciQuest | No report given. |
| PeopleAdmin | No report given. |
| NEW BUSINESS |  |
| Banner ePrint (SunGard) | Troy explained that Banner ePrint is a SunGard product, not to be confused with the independent Evisions product. ePrint is fully functional now and is housed on a separate server as a repository for reports; it is accessed using your INB login. Accessibility of reports is determined by Banner security clearance. Reports can be archived to a CD or DVD. Output from a Banner, WebFocus or Appworx report can be stored in ePrint; historical report runs are also stored and can be purged as needed. ePrint reduces or eliminates the need for printed reports and conserves physical filing space while reducing printing costs. Once security is set up, Troy will then need to define each report in ePrint. Team Leaders can forward a list of reports for their areas. ePrint will accept TXT, HTML, PDF, PPT, RTF, Excel and Word documents. Troy agreed to demo this product at the next Impl Team meeting. |
| Sign-off Form on Testing | Rick reviewed the testing sign-off form emailed by Eileen. Team Leads should forward completed forms to Troy by 2/20. A test plan or job stream can be attached in lieu of completing section 2 describing test procedures performed. |

ACTION  ITEMS

| New Action Items / Issues | Owner | Due Date | Status |
| --- | --- | --- | --- |
| NONE |  |  |  |
| Prior Items / Issues | Owner | Due Date | Current Status |
| Processing requests for reporting | Rick Marsico | ASAP | Met with IT staff and Institutional Research to develop a reporting strategy. Jim Hanek has scheduled a follow-up mtg with this group and some power users to formalize a strategy. Will address issues of inconsistency among areas interpreting the data and the need to communicate new data elements promptly. |
| Assistance for accessing TouchNet in the portal | Rick Marsico | ASAP | Only open item is the FAQ link on Stud Accts homepage. Tech Desk phone # is posted on portal homepage for users having problems logging in; a blurb regarding pop-up blockers was added. A redirect link has been added to the Stud Accts homepage. |
| Retiring CICS/Advantage subsystems | Rick Marsico | ASAP | Reporting needs have been identified for both subsystems; will move forward to address needs in order to turn off. |
| Review of portal usage policies | Bob Tupaj | ASAP | Cabinet accepted new policy re: MyYSU campus emails/announcements and Classified Ads. Ron Cole will address Impl Team at the March mtg regarding ways to communicate the new policy before implem. Troy indicated that mass mailing of MyYSU emails are not being sent 9AM-3PM to eliminate a sluggish portal. Goal is to NOT use the portal as the primary means of communication. |
| Decision document re: MyYSU email addresses for alumni and current graduates | Catherine Cala | ASAP | Catherine, Bob, Donna and Carol discussed status of SS impl for Alumni & Friends plus possibility of using a permanent email address for alumni. Will meet with Deans to discuss email options for grads, including a recom to award permanent emails to Alumni Assoc members only. Will draft decision doc and consider feasibility of conducting a survey of alumni/current grads to determine interest. |
| Classroom/Events Management Scheduling – Ad Astra | Jeanne Herman | In process | Jeanne requested a fresh instance for testing. Jason T. will provide by week of 11/17 since FinAid is still using STFA to test 7.12. Target date to have online is March/April 2009. |
| XML Transcript | Sue Davis | In process | Marie Cullen meets with the State bi-weekly regarding this mandate. |
| Evaluate if WYSU should use Banner Advancement for pledges | Advancement Team | In process | Catherine C. to meet with Kami Greene in Gen Acctg; will add finance component to decision document and resend to Impl team. |
| Requests for Labels a. Policy for departmental requests for data lists & labels for Alumni/YSU donors (centralize or decentralize) b. Create workgroup to determine responsibility for handling other departmental label requests | Catherine Cala Catherine Cala & Gen Person Team | Complete In process | Finalized policy for handling dept requests for lists/labels of alumni and YSU donors. Will continue the existing policy of processing requests using WebFocus to provide Excel spreadsheets for depts to print own labels, or Development will print labels depending on the size of the job. Will also provide a disk if requestor chooses to use a mail house. ● Need to determine a process/procedure for handling all general label requests from depts and designate the responsible area/staff to handle requests. Donna W. has been handling HR label requests; a WebFocus report should address this need in near future – ODS group must define who will write reports and who will run reports. Depts could either print their own labels or use mailroom equipment to address bulk mail pieces; will still maintain policy of 1,000 or fewer pieces. Must also have interim procedure to update M-204 and Banner with correct addresses. |
| SCT Quality Assurance Council | Project Managers | ASAP | Recommend YSU gets involved in Council to assure issues are shared/addressed. |
| Policy/procedure to create/maint. off-system mini-databases | Project Managers | Deferred | Will determine policy for departmental databases after Banner is fully implemented. |
| Reassess Banner & 3rd party software project requests and prioritize needs | Rick Marsico | Complete | Rick received replies from all areas re: Banner & 3rd party project requests & priorities. Will communicate timeline to Board at end of Feb. & modify summary sheet as priorities dictate. |

Next Meeting – Wednesday, March 18, 2009 at 9:30 a.m. in Meshel Hall, 4th floor conference room.